## WEB Excels
Daily Task Progress Report
Developer: | Date: | Project:
Fahad Bin Khalid | 15 - 16 February 2024 | Web Excels
Tasks Overview | Any blockers or challenges | Updates on tasks from last update | Current Status | Task Tracker URL
Alibaba Categories CRUD |  |  | Complete
Alibaba Services CRUD |  |  | Complete
Services Categories CRUD |  |  | Complete
Services CRUD |  |  | Complete
Portfolio with Category CRUD |  |  | Complete
WebExcels Introduction CRUD |  |  | Complete
Vision CRUD |  |  | Complete
Domain Types CRUD |  |  | Complete
Domain Pricing |  |  | Complete
Developer: | Date: | Project:
Fahad Bin Khalid | 2024-02-19 | Web Excels
Tasks Overview | Any blockers or challenges | Updates on tasks from Last update | Current Status | Task Tracker URL
Domain Info CRUD |  | I am waiting for your response to shorten this task and simplify it further, making it easier for both website administrators and users to manage. | Complete | Localhost
Alibaba Packages CRUD |  |  | Complete | Localhost
Alibaba Mini Site Packages CRUD |  |  | Complete | Localhost
Ecommerce Packages CRUD |  |  | Complete | Localhost
Alibaba Verified Packages CRUD |  |  | Complete | Localhost
Website Packages CRUD |  |  | Complete | Localhost
Developer: | Date: | Project:
Fahad Bin Khalid | 20/02/2024 | Web Excels
Tasks Overview | Any blockers or challenges | Updates on tasks from Last update | Current Status | Task Tracker URL
Upload admin dashboard on welc.pk cpanel |  | Waiting for your response to create some new features for Services and pricing |  | ( welc.pk/webexcel/login ) username: admin@gmail.com Password: qwert123
Developer: | Date: | Project:
Fahad Bin Khalid | 2024-02-21 | Web Excels
Tasks Overview | Any blockers or challenges | Updates on tasks from Last update | Current Status | Task Tracker URL
Worked on Alibaba Services, Alibaba Packages, Alibaba minisite packages and Alibaba Verified Packages forms against Categories in Jquery |  | I have modified the format of all forms on Alibaba using jQuery for easier management. | Complete | http://127.0.0.1:8000
Worked on Alibaba Services, Alibaba Packages, Alibaba minisite packages and Alibaba Verified Packages Data Tables for manage data against Categories in Jquery |  |  | Complete | http://127.0.0.1:8000
Developer: | Date: | Project:
Fahad Bin Khalid | 2024-02-22 | Web Excels
Tasks Overview | Any blockers or challenges | Updates on tasks from Last update | Current Status | Task Tracker URL
CRUD Complete for Alibaba services, Alibaba Packages, Alibaba verified Packages and Alibaba Minisite packages acoording to the new method |  | I have completed the CRUD (Create, Read, Update, Delete) operations for Alibaba services, Alibaba packages, Alibaba Minisite packages, and Alibaba Verified packages using jQuery to fetch forms. | Complete | http://127.0.0.1:8000
Developer: | Date: | Project:
Fahad Bin Khalid | 2024-02-23 | Web Excels
Tasks Overview | Any blockers or challenges | Updates on tasks from Last update | Current Status | Task Tracker URL
Alibaba Section CRUD Complete with Services and Packages in jquery against the Category |  | Alibaba Entire Sections CRUD are completed | Complete | http://127.0.0.1:8000
Start WELC Section |  | Inprogress | Pending | http://127.0.0.1:8000
Developer: | Date: | Project:
Fahad Bin Khalid | 2024-02-24 | Web Excels
Tasks Overview | Any blockers or challenges | Updates on tasks from Last update | Current Status | Task Tracker URL
Changings in Alibaba Section |  | Change the category and headings names | Complete | welc.pk/webexcel/login
Vision Section |  | Webexcels Vision section | Complete | welc.pk/webexcel/login
Webexcels Introduction Complete |  | Introduction Complete | Complete | welc.pk/webexcel/login
Developer: | Date: | Project:
Fahad Bin Khalid | 2024-02-26 | Web Excels
Tasks Overview | Any blockers or challenges | Updates on tasks from Last update | Current Status | Task Tracker URL
Ecomerce from price section |  | Done complete crud operations in it | Complete | localhost
Dynamic Website from price section |  | Done complete crud operations in it | Complete | localhost
Courses Section |  | Done complete crud operations in it | Complete | localhost
Developer: | Date: | Project:
Fahad Bin Khalid | 2024-02-27 | Web Excels
Tasks Overview | Any blockers or challenges | Updates on tasks from Last update | Current Status | Task Tracker URL
Services Category |  | Complete Total CRUD | Complete | welc.pk/webexcel/login
Service Sub Category |  | Complete Total CRUD With Conditions | Complete | welc.pk/webexcel/login
Courses Section |  | Complete Total CRUD With Conditions | Complete | welc.pk/webexcel/login
Find the link and Download Template for user interface | Waiting For Sir's Response
Developer: | Date: | Project:
Fahad Bin Khalid | 2024-02-28 | Web Excels
Tasks Overview | Any blockers or challenges | Updates on tasks from Last update | Current Status | Task Tracker URL
Portfolio Category |  | Complete Total CRUD | Complete | welc.pk/webexcel/login
Webexcels Portfolio |  | Complete Total CRUD | Complete | welc.pk/webexcel/login
Ecommerce Price |  | Complete Total CRUD | Complete | welc.pk/webexcel/login
Website Price |  | Complete Total CRUD | Complete | welc.pk/webexcel/login
Developer: | Date: | Project:
Fahad Bin Khalid | 2024-02-29 | Web Excels
Tasks Overview | Any blockers or challenges | Updates on tasks from Last update | Current Status | Task Tracker URL
Admin Side Complete |  | Complete Total Dashboard | Complete | welc.pk/webexcel/login
Setup The Frontend For Webexcels in 1 HTML |  | Implement a user interface with a video background using the default color theme in HTML | Complete | https://welc.pk/test/techex/index-3.html
Implement Frontend in Laravel directory for webexcels in blading system |  | Design and implement a user interface featuring a fresh color theme inspired by the Webexcels logo. Additionally, incorporate new images and videos showcasing the latest developments and offerings from Webexcels. | Complete | https://welc.pk/test/techex/index-3.html
Set the responsiveness |  | Ensure responsiveness in HTML and Blade formats based on the new video size. | Complete | https://welc.pk/test/techex/index-3.html
Developer: | Date: | Project:
Fahad Bin Khalid | 2024-03-01 | Web Excels
Tasks Overview | Any blockers or challenges | Updates on tasks from Last update | Current Status | Task Tracker URL
Fetch Data on Home Screen |  | Fetching the data from admin dashboard to user interface (Home Screen) | Complete | Localhost
Sections that have been completed. |  | 1. Banner Video | Complete | Localhost
Sections that have been completed. |  | 2. About Us | Complete | Localhost
Sections that have been completed. |  | 3. Why Choose Us | Complete | Localhost
Sections that have been completed. |  | 4. Our Services In Pakistan | Complete | Localhost
Sections that have been completed. |  | 5. Our Portfolio | Complete | Localhost
Sections that have been completed. |  | 6. E-Commerce & IT Business Developer | Complete | Localhost
Find an error for linux server | The GET method is not supported for route /. Supported methods: HEAD. | After 2 to 3 hours of investigation, I discovered an error on the Linux server. Further research revealed that the issue was related to the curl permissions, which were incorrectly set by the administrator. | Pending | Welc.pk/webexcel
Developer: | Date: | Project:
Fahad Bin Khalid | 2024-03-02 | Web Excels
Tasks Overview | Any blockers or challenges | Updates on tasks from Last update | Current Status | Task Tracker URL
Fetch Data on Home Screen and Company Introduction |  | Fetching the data from admin dashboard to user interface (Home Screen and Introduction Page) | Complete | Localhost
Sections that have been completed. |  | Feedback | Complete | Localhost
Sections that have been completed. |  | Clients | Complete | Localhost
Sections that have been completed. |  | Main Alibaba Services | Complete | Localhost
Sections that have been completed. |  | Frequently Asked Questions | Complete | Localhost
Sections that have been completed. |  | Webexcels Introduction | Complete | Localhost
Conditions |  | Apply Some conditions against service category, subcategory and content | Complete | Localhost
Upload Project | Composer detected issues in your platform: Your Composer dependencies require a PHP version ">= 8.2.0". | Upload Project on new hosting (webexcels.com) but there have php version issue we need a php version 8.2 something but the server have 8.1 version | Pending | webexcel.com/test/
Developer: | Date: | Project:
Fahad Bin Khalid | 2024-03-05 | Web Excels
Tasks Overview | Any blockers or challenges | Updates on tasks from Last update | Current Status | Task Tracker URL
Fetch Data on Services, Alibaba Services and Alibaba Packages |  | Fetching the data from admin dashboard to user interface (Services, Alibaba Services and Alibaba Packages) | Complete | Localhost
Sections that have been completed. |  | Services | Complete | Localhost
Sections that have been completed. |  | Alibaba Services | Complete | Localhost
Sections that have been completed. |  | Alibaba Packages | Complete | Localhost
Sections that have been completed. |  | Alibaba Verified Packages | Complete | Localhost
Sections that have been completed. |  | Alibaba Minisite Packages | Complete | Localhost
Sections that have been completed. |  | Alibaba Product Posting Packages | Complete | Localhost
Developer: | Date: | Project:
Fahad Bin Khalid | 2024-03-06 | Web Excels
Tasks Overview | Any blockers or challenges | Updates on tasks from Last update | Current Status | Task Tracker URL
Fetch Data on Feedback, Vision, Portfolio and Course Pages |  | Fetching the data from admin dashboard to user interface (Feedback, Vision, Portfolio and Course) | Complete | Localhost
Sections that have been completed. |  | Feedback | Complete | Localhost
Sections that have been completed. |  | Vision | Complete | Localhost
Sections that have been completed. |  | Portfolio in this section multiple images are fetched through single input field in array | Complete | Localhost
Sections that have been completed. |  | Course | Complete | Localhost
Developer: | Date: | Project:
Fahad Bin Khalid | 2024-03-07 | Web Excels
Tasks Overview | Any blockers or challenges | Updates on tasks from Last update | Current Status | Task Tracker URL
Job Data |  | Job Data Insert in DB From user side | Complete | Localhost
Job Data Fetch |  | Job Data Fetch On Admin Side | Complete | Localhost
Job Data Fetch |  | Job Description open when click on user details against the application id | Complete | Localhost
Navbar Categories, SubCategories and Content | Give some errors dur to the routes activity | Fetch Globally Categories, subcategories and content | Pending | Localhost
Localhost
Developer: | Date: | Project:
Fahad Bin Khalid | 2024-03-09 | Web Excels
Tasks Overview | Any blockers or challenges | Updates on tasks from Last update | Current Status | Task Tracker URL
Responsiveness |  | Responsiveness correction complete | Complete | http://welc.pk/webexcel/
Aboutus |  | Aboutus section complete | Complete | http://welc.pk/webexcel/
Vision |  | Vision complete | Complete | http://welc.pk/webexcel/
Jobs |  | Jobs complete | complete | http://welc.pk/webexcel/
Storage |  | Storage linked complete | complete | http://welc.pk/webexcel/
Developer: | Date: | Project:
Fahad Bin Khalid | 2024-03-11 | Web Excels
Tasks Overview | Any blockers or challenges | Updates on tasks from Last update | Current Status | Task Tracker URL
Services |  | Services with Prices | Complete | http://welc.pk/webexcel/
Ecommerce Price in Service Section |  | With Service Category | Complete | http://welc.pk/webexcel/
Social media marketing Section |  | With Service Category | Complete | http://welc.pk/webexcel/
Domain And Hosting |  | With Service Category | complete | http://welc.pk/webexcel/
Developer: | Date: | Project:
Fahad Bin Khalid | 2024-03-27 | Web Excels
Tasks Overview | Any blockers or challenges | Updates on tasks from Last update | Current Status | Task Tracker URL
Add Section For SEO |  | Create keywords dezcription for SEO | Complete | http://welc.pk/webexcel/
Some changings in home page |  | Alibaba section Delete from Home Page | Complete | http://welc.pk/webexcel/
Fix Some Bugs |  | Entire website | Complete | http://welc.pk/webexcel/

## Customer Support
Daily Task Progress Report
Developer: | Date: | Project:
Zunair Bin Ahmad | 2024-01-26 | Customer Support
Tasks Overview | Any blockers or challenges | Updates on tasks from last update | Current Status | Task Tracker URL
I worked on developing a user-side dashboard to retrieve data from an API and fetch information for 3000 users from the database.
Additionally, I focused on testing the authentication process to ensure its proper functionality. Furthermore, I conducted testing for user interactions on the messenger platform.
I collaborated with Afaq to obtain project details through an API and implemented some modifications.
Similarly, I worked on two other APIs, making necessary improvements and adjustments.
Developer: | Date: | Project:
Zunair Bin Ahmad | 19-02-24 | Customer Support
Tasks Overview | Any blockers or challenges | Updates on tasks from last update | Current Status | Task Tracker URL
Worked on user Complain Section on select menu get data from api in it |  | Get customer api and payment api matched Authenticated user email with customer api email and get matched row id then matched this id with payment api com_id and get all matched data rows then filter its services/projects name and show in select menu | complete | http://127.0.0.1:8000/usercomplain
Project details page | Need department manager data in team member api & Project duration time in project api |  | pending | http://127.0.0.1:8000/projectdetail
Invoice page data |  | remove unnecessary data and change sequence of remaining data | complete | http://127.0.0.1:8000/user/payment
Developer: | Date: | Project:
Zunair Bin Ahmad | 20-02-24 | Customer Support
Tasks Overview | Any blockers or challenges | Updates on tasks from last update | Current Status | Task Tracker URL
change logo |  | change logo from welc to webexcels logo | complete | https://webhostingserverusa.com/admindashboard
Project Details | waiting for api changes |  | pending | https://webhostingserverusa.com/projectdetail
Files section |  | complete with proper file validation add some instruction which files required | complete | https://webhostingserverusa.com/file
Admin side Client data |  | Show all data with format and show uploading files there | complete | https://webhostingserverusa.com/admin/projectform
Developer: | Date: | Project:
Zunair Bin Ahmad | 21-02-24 | Customer Support
Tasks Overview | Any blockers or challenges | Updates on tasks from last update | Current Status | Task Tracker URL
Team late messages section |  | reconstruct controller and methods to fetch late replies properly | complete | https://webhostingserverusa.com/admin/chats/chatsfetch
Project Details | waiting for api changes |  | pending | https://webhostingserverusa.com/projectdetail
Developer: | Date: | Project:
Zunair Bin Ahmad | 22-02-24 | Customer Support
Tasks Overview | Any blockers or challenges | Updates on tasks from last update | Current Status | Task Tracker URL
Team late messages section with details | just counter condition issue | Fetch data according to team late messages | pending | https://webhostingserverusa.com/admin/chats/chatsfetch
Project Details | waiting for api changes |  | pending | https://webhostingserverusa.com/projectdetail
Developer: | Date: | Project:
Zunair Bin Ahmad | 2024-02-23 | Customer Support
Tasks Overview | Any blockers or challenges | Updates on tasks from last update | Current Status | Task Tracker URL
Team late messages | Conlifict in Late messages | Fetch data according to team late messages | pending | Localhost
Developer: | Date: | Project:
Zunair Bin Ahmad | 2024-02-24 | Customer Support
Tasks Overview | Any blockers or challenges | Updates on tasks from last update | Current Status | Task Tracker URL
Team late messages |  | team members late messages fetched accuratly reconstruct the method with new conditions and implement it into application | Complete | https://webhostingserverusa.com/admin/chats/chatsfetch
Testing |  | testing it through different sessions and it work perfectly | Complete | https://webhostingserverusa.com/admin/chats/chatsfetch
Developer: | Date: | Project:
Zunair Bin Ahmad | 2024-02-26 | Customer Support
Tasks Overview | Any blockers or challenges | Updates on tasks from last update | Current Status | Task Tracker URL
Team late messages on team dashboard |  | make frontend section for team dashboard show authenticated team member to his own late replies count on his dashboard | Complete | https://webhostingserverusa.com/teamdashboard/admin/chats/chatsfetch
Team late messages on admin |  | show every team member in list and show their late replies count in the front of his name to easily noticing for admin | Complete | https://webhostingserverusa.com/admin/chats/chatsfetch
testing |  | tested every module by its session | Complete
Developer: | Date: | Project:
Zunair Bin Ahmad | 2024-02-27 | Customer Support
Tasks Overview | Any blockers or challenges | Updates on tasks from last update | Current Status | Task Tracker URL
Team late messages |  | make time pickers to select from and to time design it according to template | Complete | https://webhostingserverusa.com/teamdashboard/admin/chats/chatsfetch
Team late messages |  | Done backend according to its functionality | Complete | https://webhostingserverusa.com/teamdashboard/admin/chats/chatsfetch
Team late messages |  | make a section for reasoning of teammember late reply | Complete | https://webhostingserverusa.com/teamdashboard/admin/chats/chatsfetch
Team late messages |  | testing | Complete | https://webhostingserverusa.com/teamdashboard/admin/chats/chatsfetch
Developer: | Date: | Project:
Zunair Bin Ahmad | 2024-02-28 | Customer Support
Tasks Overview | Any blockers or challenges | Updates on tasks from last update | Current Status | Task Tracker URL
Team late messages team dashboard |  | add input fields to end of every row | Complete | https://webhostingserverusa.com/teamdashboard
Team late messages team dashboard |  | Done backend according to its functionality | Complete | https://webhostingserverusa.com/teamdashboard
Team late messages team dashboard |  | make database table and models set according to it | Complete | https://webhostingserverusa.com/teamdashboard
Team late messages |  | post data into db | Complete | https://webhostingserverusa.com/teamdashboard
Developer: | Date: | Project:
Zunair Bin Ahmad | 2024-02-29 | Customer Support
Tasks Overview | Any blockers or challenges | Updates on tasks from last update | Current Status | Task Tracker URL
Team late messages admin dashboard |  | add section to end of every row to show reasons | Complete | https://webhostingserverusa.com/admin/chats/chatsfetch
Team late messages admin dashboard |  | Done backend according to its functionality by matching id | Complete | https://webhostingserverusa.com/admin/chats/chatsfetch
Team late messages admin dashboard |  | testing it | Complete | https://webhostingserverusa.com/admin/chats/chatsfetch
Developer: | Date: | Project:
Zunair Bin Ahmad | 2024-03-01 | Customer Support
Tasks Overview | Any blockers or challenges | Updates on tasks from last update | Current Status | Task Tracker URL
Chat system |  | working on logic building and testing of auto reply in case of late reply to user | pending | https://webhostingserverusa.com/chat/chatify
Developer: | Date: | Project:
Zunair Bin Ahmad | 3/5/2024 , 3/6/2024 | Customer Support
Tasks Overview | Any blockers or challenges | Updates on tasks from last update | Current Status | Task Tracker URL
Chat system |  | working on implementation of logic | 80% complete | https://webhostingserverusa.com/chat/chatify
Developer: | Date: | Project:
Zunair Bin Ahmad | 2024-03-07 | Customer Support
Tasks Overview | Any blockers or challenges | Updates on tasks from last update | Current Status | Task Tracker URL
Chat system |  | working on implementation of logic | complete | https://webhostingserverusa.com/chat/chatify
Design |  | Implement design according to theme | complete | https://webhostingserverusa.com/chat/chatify
Testing |  | testing it properly with time delay | complete | https://webhostingserverusa.com/chat/chatify
Developer: | Date: | Project:
Zunair Bin Ahmad | 2024-03-09 | Customer Support
Tasks Overview | Any blockers or challenges | Updates on tasks from last update | Current Status | Task Tracker URL
Chat system |  | working on team and user sessions to manage timer to show alert | complete | https://webhostingserverusa.com/chat/chatify
Design |  | Implement design according to theme | complete | https://webhostingserverusa.com/chat/chatify
Testing |  | testing it properly with time delay | complete | https://webhostingserverusa.com/chat/chatify
User Dashboard |  | Changes navbar text
Developer: | Date: | Project:
Zunair Bin Ahmad | 2024-03-27 | Customer Support
Tasks Overview | Any blockers or challenges | Updates on tasks from last update | Current Status | Task Tracker URL
User Dashboard |  | Create a new page layout and add a button give route to complain section | complete | https://webexcels.com/customersupport/usercomplain
User Dashboard |  | get api that is required for fields to show user | complete | https://webexcels.com/customersupport/usercomplain
User Dashboard |  | make methods to fetch those api's | complete | https://webexcels.com/customersupport/usercomplain
User Dashboard |  | Get team api and fetch it get all team members name from it and show it in my view in select menu form . | complete | https://webexcels.com/customersupport/usercomplain
User Dashboard |  | Get customer api fetch it get all (com_id) from it and show after filter by matched it with authenticated persons credentials and only just show in input form which user is currently loged in. | complete | https://webexcels.com/customersupport/usercomplain
User Dashboard |  | Get team api and fetch it get all departments name and remove repeated names . | complete | https://webexcels.com/customersupport/usercomplain
User Dashboard |  | make priority select menu | complete | https://webexcels.com/customersupport/usercomplain
User Dashboard | wait for more api's for fetch service |  |  | https://webexcels.com/customersupport/usercomplain